## Sheet1
Legend:
| Project Start Date: | 2022-10-24 |  |  | On Track |  |  |  | Low Risk |  |  |  | Med Risk |  |  |  | High Risk
Gantt Chart
[5 empty] | October | [6 empty] | November | [27 empty] | December
[5 empty] | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
[5 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
Milestone Description | Category | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Set up a web application and database structure | On Track | 100% | 2022-10-17 | 4 | bar: October 24 to October 27
Set up backend and routes | Low Risk | 100% | 2022-10-31 | 1 | bar: November 31
Create user dashboard | Low Risk | 80% | 2022-11-01 | 2 | bar: November 1 to November 2
Create a nutrition module | Med Risk | 60% | 2022-11-03 | 5 | bar: November 3 to November 4; November 7 to November 8; November 15 to November 16
Create an activity module | Med Risk | 60% | 2022-11-11 | 4 | bar: November 9 to November 11; November 14
Create a measurement module | Low Risk | 0% | 2022-11-17 | 2 | bar: November 17 to November 18
Link all the modules above in dashboard | Low Risk | 0% | 2022-11-21 | 1 | bar: November 21
Authentication module: login and register | Low Risk | 0% | 2022-11-22 | 2 | bar: November 22 to November 23
Create an appointment module | High Risk | 0% | 2022-11-24 | 4 | bar: November 24 to November 25; December 28 to December 30